## Accounts Inventory
ID | Type | Item | Entry Point | v2 Source Path | What The User Does | Key UI Elements | API Endpoint(s) | Permission / Role Gate | Traffic Priority | Port Decision | Status | Owner | Target | Notes / Gaps
ACC-01 | Screen | Accounts List | /admin/accounts ¦ /user/accounts Nav: 'Accounts'. Also the user-persona post-login landing when the user belongs to >1 account. | src/modules/Accounts/containers/index.js src/modules/Accounts/components/index.js | Browse, search and filter every account the user can see; switch the app's account context (enter an account); run per-account lifecycle actions. | Composed of 4 regions: header band, filter side panel, table, row action menu. | GET /v2/core/accounts?page&limit&key&my_account&new_account_flag&sort_by&order&status&org_id&users | Route accessKey 'accounts', checked against userPermission.nav_menu_list in routes/components/AuthPage.js | P0 | Port as-is | Not Started | The ONLY screen in the module. No nested routes and no AntD Tabs anywhere in modules/Accounts.
ACC-02 | Region | Header band | Top of the Accounts List screen | src/modules/Accounts/components/AccountsHeader/index.js | Switch between the three list modes, open the advanced filter panel, start a new account. | Segmented Button.Group used as de-facto tabs: New Accounts (my_account=0) / My Accounts (=1, default) / All Accounts (=2). Deactivation alert banner 'N Account has requested deactivation'. Advanced-filter toggle. 'New Account' button. Suspended-account message. | Drives the my_account / new_account_flag params on the list endpoint | Whole group only for isSuperAdmin ¦¦ isOnboardingAdmin ¦¦ isCSAdmin ¦¦ isOnlyXPAAdmin. 'All Accounts' hidden for isOnlyXPAAdmin. Banner needs isSuperAdmin===1 && deactivationRequestCount. 'New Account' needs userPermission.account includes 'create'. | P0 | Redesign | Not Started | Button.Group is doing a tab's job. On the new shell make it a real segmented control / tabs.
ACC-03 | Region | Filter side panel | Advanced-filter toggle in the header band | src/modules/Accounts/components/AccountsSearchFilter/index.js src/modules/Accounts/components/AccountsSearchFilter/InfiniteScrollDropdown.js src/modules/Accounts/components/AccountsSearchFilter/DropdownOptions.js | Narrow the account list by free text, organization, status and username. | Rendered in SidePanelCard titled 'Filter Accounts' with a global Clear. Search (debounced 800ms, placeholder 'E.g: California'). Organization: paginated infinite-scroll dropdown. Status: multi-select. Username: debounced search. | GET /v2/core/organizations/get_organizations?key&status=0,1&limit=300&type=accounts_filter | Organization filter: isAdmin only. Username filter: isAdmin && currentRole !== 'Sales Admin'. | P0 | Port as-is | Not Started | Status values are raw numeric codes: Active=1, Inactive=-1, Deactivation requested=3, Onboarding=0, Suspended=-3. Map these explicitly on the new shell.
ACC-04 | Region | Accounts table | Body of the Accounts List screen | src/modules/Accounts/components/AccountsList/index.js src/modules/Accounts/components/AccountsList/partials/OnboardingInfo.js src/modules/Accounts/components/AccountsList/partials/MismatchCount.js | Read account state at a glance, enter an account, jump to that account's mismatches. | AntD Table id='accountslist_table'. 7 columns: Accounts (name link enters the account; sortable; EX tag for exception accounts; deactivation icon for superadmin on status 3), Tiers, Users, Info (Onboarding badge + Mismatches badge), Activated On (sortable), Status (sortable), Action. Footer: Pagination + page-size dropdown, shown only when accountCount > 10. No row selection. | Same list endpoint; sorting via sort_by & order params | Tier Managers cannot open suspended accounts - the name renders as plain text and View is disabled. | P0 | Port as-is | Not Started | No bulk actions and no export exist anywhere in this module - see GAP-09 before assuming that is intentional.
ACC-05 | Region | Row action menu | 'Action' column on each table row | src/modules/Accounts/components/AccountsList/partials/ActionItem.js | Run per-account admin lifecycle actions. | 11 permission-gated items: Account Settings, Mark as Exception, Remove as Exception, Configure Bundles, Configure Products, Duplicate Account, Assign Manager, Edit Account, Suspend Account, Reactivate Account, Activate. For status===3 the row shows a single Accept/Reject button instead of the menu. | Each item dispatches its own call - see the drawer rows below | Per item, from userPermission.account: setting, mark_exception, remove_exception, bundles, duplicate, activate, activate_onboarding; plus editPermission and isSuperAdmin. Every item is disabled when !isSuperAdmin && item.status===-3. | P0 | Redesign | Not Started | 11 gated items behind one dropdown. Parity of capability, not layout - split into inline primary actions plus an overflow menu (GAP-12).
ACC-06 | Drawer | New Account | 'New Account' button in the header band (id=newaccount_drawer) | src/modules/Accounts/components/AccountsHeader/partials/NewAccountDrawer.js src/modules/Accounts/components/AccountsHeader/partials/NewAccount.js | Create a new account. | Fields: account name, Vertical, category, Products & Services (ServicesDropdown), Blueprint, Organization, Country, Time Zone (options depend on Country), Date Format (auto-derived). | POST /v2/core/accounts GET /v2/core/verticals?key&limit=2000&source=UI GET /v2/prl/country | userPermission.account includes 'create' | P0 | Port as-is | Not Started | Time Zone list is dependent on the selected Country - keep that dependency on the new shell.
ACC-07 | Inline section | New Account > Create New Organization | 'Create New' option inside the Organization dropdown of ACC-06 | src/modules/Accounts/components/AccountsHeader/partials/NewAccountOrg.js | Create an organization inline without leaving the new-account flow. | Fields: organization name, contact name, contact email, contact number, Onboarding Owner. | Submitted as part of the POST /v2/core/accounts payload | isSuperAdmin ¦¦ isOnboardingAdmin. Hidden in duplicate mode. Entire block skipped for isOrgManager. | P1 | Port as-is | Not Started | Nested creation inside a creation form - verify this is still wanted before reproducing it.
ACC-08 | Inline section | New Account > Add New Manager | Toggle inside the ACC-06 drawer body | src/modules/Accounts/components/AccountsHeader/partials/NewAccount.js | Create the account's first manager inline. | Fields: first name, last name, email, phone (country-aware validation). | POST /v2/core/users | Inherits the ACC-06 'create' gate | P1 | Port as-is | Not Started | Phone validation is country-aware via react-international-phone + libphonenumber-js.
ACC-09 | Drawer | Duplicate Account | Row action menu > Duplicate Account (id=duplicateaccount_drawer) | src/modules/Accounts/components/AccountsHeader/partials/NewAccountDrawer.js (duplicate mode) | Clone an existing account's configuration into a new account. | Same form as ACC-06; the title and several fields switch to read-only duplicate mode and prefill from selectedAccountInfo. | GET /v2/core/accounts/{accountId} POST /v2/core/accounts | userPermission.account includes 'duplicate' | P1 | Port as-is | Not Started | Same component as ACC-06 in a different mode - port once with two modes, do not build twice.
ACC-10 | Drawer | Edit Account | Row action menu > Edit Account (id=accountedit_drawer) | src/modules/Accounts/components/AccountsList/partials/EditAccount.js | Edit an existing account's core attributes. | Fields: Name, Vertical, category, services, Blueprint (disabled), Country (disabled), Time Zone (enabled only for superadmin), Date Format (disabled). Vertical and category are locked when the account is Finance > Bank. | GET /v2/core/accounts/{accountId} PUT /v2/core/accounts/{accountId} | editPermission ¦¦ currentRole === 'Organization Manager', and item.status !== 1 | P0 | Redesign | Not Started | 4 of 7 fields are permanently disabled - a bad screen to reproduce faithfully. See GAP-10.
ACC-11 | Drawer | Activate Account | Row action menu > Activate (id=accountactivation_drawer) | src/modules/Accounts/components/AccountsList/partials/ActivateAdminAccount.js | Confirm activation of an onboarding or inactive account. | Confirmation dialog; on confirm calls AccountStatus({status: 1}). | PUT /v2/core/accounts/{id}/activate | (activate ¦¦ activate_onboarding) + item.status is 0 or -1 | P1 | Redesign | Not Started | Duplicate capability with ACC-12 reached by a different route - collapse the two (GAP-08).
ACC-12 | Drawer | Account Status - Onboarding | 'Onboarding' badge in the table's Info column | src/modules/Accounts/components/index.js:389-415 src/modules/Accounts/components/AccountsList/partials/ActivateAccount.js | A second, separate activate flow for onboarding accounts. | Drawer titled 'Account Status - Onboarding' with Cancel / Activate footer. | PUT /v2/core/accounts/{id}/activate | canActivateOnboardingAccount (userPermission.account includes 'activate_onboarding') | P1 | Redesign | Not Started | Same outcome as ACC-11 via a different entry point and a different component. Merge on the new shell.
ACC-13 | Drawer | Account Deactivation Request | Deactivation icon on the row, or the Accept/Reject button shown on status===3 rows (id=accountdeactivation_drawer) | src/modules/Accounts/components/index.js:416-462 src/modules/Accounts/components/DeactivationDrawer/index.js | Superadmin approves or rejects a tenant's request to deactivate their account. | Warning list of consequences, Approve/Reject radio, reason textarea (mandatory when rejecting), 'Yes, Confirm' footer. | PUT v2/core/accounts/{id}/deactivate?flag=confirm_deactivation¦reject_deactivation | isSuperAdmin===1 && currentUser.id !== item.deactivated_request_id | P1 | Port as-is | Not Started | The self-approval block (a superadmin cannot action their own request) is real business logic - keep it.
ACC-14 | Drawer | Add / Remove Exception | Row action menu > Mark as Exception / Remove as Exception (id=addremoveexception_drawer) | src/modules/Accounts/components/AccountsList/partials/AccountExceptions/index.js src/modules/Accounts/components/AccountsList/partials/AccountExceptions/ExceptionHandler.js | Flag or unflag an account as an exception account. | Confirmation drawer with AlertBox; the flag surfaces as an 'EX' tag in the table's Accounts column. | PUT /v2/core/accounts/{accountId} body: {account: {is_exception}} | mark_exception / remove_exception + item.status is 0 or 1 | P2 | Port as-is | Not Started | Mounted at the screen root and driven by the currentExceptionHandler state object rather than local row state.
ACC-15 | Drawer | Suspend / Reactivate Account | Row action menu > Suspend Account / Reactivate Account (id=suspend-reactivate-account) | src/modules/Accounts/components/AccountsList/partials/AccountSuspension/index.js src/modules/Accounts/components/AccountsList/partials/AccountSuspension/SuspendReactivate.js | Suspend an active account, or reactivate a suspended one. | Mandatory reason textarea; the reason is surfaced later as a tooltip on the Status column. | PUT /v2/core/accounts/{accountId}/suspend ¦ /activate_suspended body: {request_reason} | isSuperAdmin===1. Suspend requires status===1; Reactivate requires status===-3. | P1 | Port as-is | Not Started | Suspension puts the whole account into a read-only state elsewhere in the app (getIsSuspendedAccount) - that knock-on must survive the port.
ACC-16 | Modal | Assign Account Manager | Row action menu > Assign Manager (id=accountmanagerassign_modal) | src/modules/Accounts/components/AccountsList/partials/AssignManagerModal.js | Assign a manager to the account from within the account's organization. | AntD Modal with a debounced user search scoped to the account's organization. | GET /v2/core/organizations/{id}/users?page&limit&key | editPermission ¦¦ currentRole === 'Organization Manager', and item.status !== 1 | P1 | Port as-is | Not Started | Supersedes the orphaned ManagerAssign.js (ACC-23).
ACC-17 | Cross-module dep | Account Settings drawer | Row action menu > Account Settings | src/modules/AccountSettings/containers (opened from src/modules/Accounts/components/AccountsList/partials/ActionItem.js:419) | Opens the shared Account Settings drawer over the Accounts List. | Owned by the AccountSettings module: 9 collapsible panels plus a 'Review Changes' diff state, and 2 sibling drawers. | GET/PUT /v2/core/accounts/{id}/settings | userPermission.account includes 'setting' | P0 | Needs decision | Not Started | NOT owned by this module - gets its own inventory round. The Accounts port is blocked on it for full parity.
ACC-18 | Cross-module dep | Configure Products drawer | Row action menu > Configure Products | src/modules/Organizations/components/partials/ConfigureDrawer/index.js (opened from ActionItem.js:456) | Configure the products enabled for the account. | Owned by the Organizations module. | Organizations module endpoints | editPermission (authSelector.getAdminEditPermission) | P1 | Needs decision | Not Started | Shared with Organizations - decide who ports it so it is not built twice.
ACC-19 | Cross-module dep | Configure Bundles | Row action menu > Configure Bundles - navigates to /{admin¦user}/account/bundles | src/modules/Bundles (route at routes/config/admin.js:140, user.js:244) | Leaves the Accounts screen for the Bundles module. | A route navigation, not a drawer. | Bundles module endpoints | userPermission.account includes 'bundles' | P2 | Needs decision | Not Started | Exit point from this module - only the menu item and its gate belong to the Accounts port.
ACC-20 | Dead code | Sync to V1 drawer | NONE - no live trigger | src/modules/Accounts/components/index.js:354-388 src/modules/Accounts/components/SyncToV1/index.js | Was: sync an account to V1 and show sync errors. | Drawer is still rendered on every page load, but nothing can open it. | Actions syncToV1 / updateSyncStatus still wired in actions.js + reducer.js | n/a | P2 | Drop | Excluded | VERIFIED DEAD: onSync and onAccountSync are commented out of the consumer's props at AccountsList/index.js:95 and :98. See GAP-01.
ACC-21 | Dead code | Assign Admin modal (Customer Success Admin) | NONE - no live trigger | src/modules/Accounts/components/AccountsList/partials/AssignAdminModal.js | Was: assign a Customer Success Admin to the account. | Modal is rendered and its open handler is defined, but the handler is never invoked. | n/a | n/a | P2 | Drop | Excluded | VERIFIED DEAD: ActionItem.js:361 passes onClick={onAssignClick} to ActionMenu, and ActionMenu (ActionItem.js:40-64) never destructures onClick. See GAP-02.
ACC-22 | Dead code | Deactivate Account drawer | NONE - no live trigger | src/modules/Accounts/components/AccountsList/partials/DeactivateAccount.js | Was: directly deactivate an account. | Drawer is rendered and its setter is forwarded, but no menu item invokes it. | n/a | n/a | P2 | Drop | Excluded | VERIFIED DEAD: ActionItem.js:374 passes setShowDeactivateAccount to ActionMenu, which never destructures it. Deactivation now runs through the request/approve flow (ACC-13). See GAP-03.
ACC-23 | Dead code | ManagerAssign.js (orphan file) | NONE - file is never imported | src/modules/Accounts/components/AccountsList/partials/ManagerAssign.js | Was: an 'Assign Account Manager' drawer with an add/remove admin list. | 225 lines, unreferenced. | n/a | n/a | P2 | Drop | Excluded | VERIFIED DEAD: zero imports repo-wide. Superseded by AssignManagerModal.js (ACC-16). See GAP-04.
ACC-24 | Dead code | SyncStatus.js (orphan file) | NONE - file is never imported | src/modules/Accounts/components/AccountsList/partials/SyncStatus.js | Was: the 'Not Synced' badge button that opened the Sync to V1 drawer. | 27 lines, unreferenced. | n/a | n/a | P2 | Drop | Excluded | VERIFIED DEAD: zero imports repo-wide. Removing this is what stranded ACC-20. See GAP-05.

## Gaps & Decisions
Gaps found while taking the inventory - written down now rather than discovered later
ID | Finding | Evidence (file:line) | Type | Recommendation | Decision | Decided By | Date
GAP-01 | Sync to V1 drawer is rendered on every page load but has no reachable trigger | src/modules/Accounts/components/index.js:354-388 vs src/modules/Accounts/components/AccountsList/index.js:95,98 | Dead code | Do not port. Also remove the syncToV1 / updateSyncStatus actions and their reducer state, which are still wired.
GAP-02 | Assign Admin ('Customer Success Admin') modal can never open | src/modules/Accounts/components/AccountsList/partials/ActionItem.js:361 vs :40-64 | Dead code | Do not port. Confirm with Geetha that CS-Admin assignment is not a capability users lost silently.
GAP-03 | Deactivate Account drawer can never open | src/modules/Accounts/components/AccountsList/partials/ActionItem.js:374 vs :40-64 | Dead code | Do not port. Deactivation is handled by the request/approve flow (ACC-13).
GAP-04 | ManagerAssign.js is an orphan - zero imports repo-wide | src/modules/Accounts/components/AccountsList/partials/ManagerAssign.js | Dead code | Do not port. Superseded by AssignManagerModal.js.
GAP-05 | SyncStatus.js is an orphan - zero imports repo-wide | src/modules/Accounts/components/AccountsList/partials/SyncStatus.js | Dead code | Do not port. Its removal is what stranded the Sync to V1 drawer.
GAP-06 | /admin/account and /user/account (singular) render a blank page | src/routes/config/admin.js:169 ¦ src/routes/config/user.js:261 | Dead route | Do not port the route. It maps to the AccountSettings drawer container with no showAccountSetting prop, so it renders an empty fragment.
GAP-07 | /user/accounts is declared twice in the nav as 'Accounts' and 'Org Accounts' | src/modules/Nav/userNavItems.js:105 and :116; resolved at Nav/components/index.js:992-1013 | Duplicate | Ship one nav entry with a role-dependent label instead of two entries competing for the same path.
GAP-08 | Two separate activate flows exist for the same outcome | ActivateAdminAccount.js (row menu) vs ActivateAccount.js via src/modules/Accounts/components/index.js:389-415 (Onboarding badge) | Redesign | Collapse into a single activate flow with one entry point. Parity of capability, not of layout.
GAP-09 | The module has no bulk actions and no export anywhere | Whole module - src/modules/Accounts/components/AccountsList/index.js has no row selection | Product decision | Confirm this is intentional. For the largest-inventory product this looks like a capability gap worth closing during the port, not a parity item to preserve.
GAP-10 | Edit Account shows 7 fields of which 4 are permanently disabled | src/modules/Accounts/components/AccountsList/partials/EditAccount.js | Redesign | Either make Blueprint / Country / Date Format editable, or stop rendering them as dead inputs. Reproducing this faithfully is the failure mode named in the brief.
GAP-11 | Accounts style and partial files are imported by other modules | Imported by Organizations, UserManagement, Profile, Hierarchy and Settings | Constraint | Do not delete Accounts files when the module is ported. Shared pieces must be extracted first or those modules break.
GAP-12 | Row action menu carries 11 permission-gated items in a single dropdown | src/modules/Accounts/components/AccountsList/partials/ActionItem.js | Redesign | Split into 2-3 inline primary actions plus an overflow menu. Decide the primary set from traffic data.

## Progress & Legend
XMP Port - Accounts Module Progress
All figures are live formulas over the 'Accounts Inventory' tab. Update Status there; this updates itself.
Headline
Total items inventoried
In scope (excludes Excluded)
Done
% complete (in scope)
P0 items not yet Done
Open gaps awaiting a decision
By Status | Count | % of total
Not Started
In Progress
In Review
Done
Blocked
Excluded
By Traffic Priority | Count | Not Done
P0
P1
P2
By Port Decision | Count
Port as-is
Redesign
Drop
Needs decision
Legend
Status
Not Started |  |  | Inventoried, not begun.
In Progress |  |  | Being built on the new shell.
In Review |  |  | Built; awaiting parity check against v2.
Done |  |  | At capability parity on the new shell, verified against v2.
Blocked |  |  | Cannot proceed - reason goes in Notes / Gaps.
Excluded |  |  | Deliberately not ported (dead code, or a decision recorded on the Gaps tab).
Traffic Priority
P0 |  |  | Top-traffic - sequence these first. The brief says sequence by traffic, not by screen order.
P1 |  |  | Regular use.
P2 |  |  | Rare or administrative.
Port Decision
Port as-is |  |  | Capability and flow are sound; reproduce the capability on the new shell.
Redesign |  |  | Capability must survive, the flow must not. Parity is the floor, not the ceiling.
Drop |  |  | Do not carry forward. Requires a recorded decision on the Gaps tab.
Needs decision |  |  | Owner or approach unresolved - resolve before the screen is scheduled.
The rule this sheet enforces
Parity is the floor |  |  | Parity of capability, not of layout. Reproducing a bad screen faithfully is the failure mode. Nothing may be silently dropped - if it is not ported, it is written down on the Gaps tab.
Scope: v2/src/modules/Accounts only. AccountSettings and the wider /account/* route namespace are separate inventories.
Source: /Users/ashwanidohray/Github2026/v2 (branch checked at time of inventory). Dead-code findings verified by reading source, not inferred.