## XMP Inventory P1
Area | Existing screen/flow | Parity required | New shell | Status | Type | Entry point (URL) | Persona | Permission / feature gate | v2 source path | Traffic rank | Notes / Gap
Accounts | Accounts | Yes | ⬜ | Not Started | Page | /admin/accounts | Admin | accessKey: accounts | modules/Accounts/containers | P0
Accounts | Accounts | Yes | ⬜ | Not Started | Page | /user/accounts | User / Agent / Org / Tier | accessKey: accounts | modules/Accounts/containers | P0 | Declared landing route (user DEFAULT_ROUTES.AUTHED_ROUTE).
AgentDashboard | AgentDashboard | Yes | ⬜ | Not Started | Page | /user/account/user-dashboard | User / Agent / Org / Tier | accessKey: dashboard | modules/AgentDashboard/containers | P0 | Declared landing route (user DEFAULT_ROUTES.AGENT_BASE_ROUTE).
AgentReviews | AgentReviews | Yes | ⬜ | Not Started | Page | /user/account/reviews | User / Agent / Org / Tier | accessKey: reviews_management ¦ app: pc_enable_3rd_party_review_mgmt ¦ isForAgent: true ¦ componentId: agent_reviews_management | modules/AgentReviews/containers | P0 | Two intentional entries (agent vs non-agent). Latent bug: both share React key '/account/reviews' when isAgentLogin is true (AuthRouter.js:159).
Auth | AdminSignInPage | Yes | ⬜ | Not Started | Anonymous page | /admin/signin | Admin | Public | modules/Auth/containers/AdminIndex | P0 | Declared landing route (admin DEFAULT_ROUTES.BASE_ROUTE).
Auth | SSOAuth | Yes | ⬜ | Not Started | Page | /sso_callback | All | None (authenticated only) | modules/Auth/containers/SSOAuthIndex | P0
Auth | PrivacyAgreement | Yes | ⬜ | Not Started | Anonymous page | /user/privacy-agreement | User / Agent / Org / Tier | Public | modules/Auth/components/UserSignInSignUp/ThirdPartySignup/PrivacyAgreement | P0 | Declared landing route (user DEFAULT_ROUTES.SSO_LICENSE_ROUTE).
Auth | UserProfileSetup | Yes | ⬜ | Not Started | Page | /user/profile-setup | User / Agent / Org / Tier | None (authenticated only) | modules/Auth/components/UserProfileSetup/containers | P0 | Declared landing route (user DEFAULT_ROUTES.PROFILE_SETUP_ROUTE).
Auth | UserSignIn | Yes | ⬜ | Not Started | Anonymous page | /user/signin | User / Agent / Org / Tier | Public | modules/Auth/components/UserSignInSignUp/SignIn/index.js | P0 | Declared landing route (user DEFAULT_ROUTES.BASE_ROUTE).
Auth | UserSignInPage | Yes | ⬜ | Not Started | Anonymous page | /xpa/signin | XPA | Public | modules/Auth/containers/UserIndex | P0 | Declared landing route (xpa DEFAULT_ROUTES.BASE_ROUTE).
Hierarchy | Hierarchy | Yes | ⬜ | Not Started | Page | /admin/account/hierarchy | Admin | accessKey: hierarchy | modules/Hierarchy/containers | P0 | Declared landing route (admin DEFAULT_ROUTES.CONTEXT_SELECTED_ROUTE).
Hierarchy | Hierarchy | Yes | ⬜ | Not Started | Page | /user/account/hierarchy | User / Agent / Org / Tier | accessKey: hierarchy | ../../modules/Hierarchy/containers | P0
Hierarchy | Hierarchy | Yes | ⬜ | Not Started | Page | /user/account/hierarchy/:id | User / Agent / Org / Tier | accessKey: hierarchy | ../../modules/Hierarchy/containers | P0
HierarchyDashboards | HierarchyDashboards | Yes | ⬜ | Not Started | Page | /admin/account/dashboard | Admin | accessKey: dashboard | modules/HierarchyDashboards/containers | P0 | Declared landing route (admin DEFAULT_ROUTES.DASHBOARD_ROUTE).
HierarchyDashboards | HierarchyDashboards | Yes | ⬜ | Not Started | Page | /user/account/dashboard | User / Agent / Org / Tier | accessKey: dashboard | modules/HierarchyDashboards/containers | P0 | Declared landing route (user DEFAULT_ROUTES.TIER_BASE_ROUTE).
Listing | ListingCustomerDashboard | Yes | ⬜ | Not Started | Page | /user/account/listing/dashboard | User / Agent / Org / Tier | accessKey: listings ¦ app: pc_enable_listings | modules/Listing/submodules/CustomerListingDashboard/container | P0 | Declared landing route (user DEFAULT_ROUTES.LISTING_MGR_BASE_ROUTE).
Nav | Nav (left menu + header chrome) | Yes | ⬜ | Not Started | Global chrome | n/a - mounted by AuthRouter.js:8 | All | getAccess() per item | modules/Nav | P0 | 247 nav path entries across admin/user/agent. Permission gating lives here as well as in AuthPage - port as ONE concept.
Organizations | Organizations | Yes | ⬜ | Not Started | Page | /admin/organizations | Admin | accessKey: organizations | modules/Organizations/containers | P0 | Declared landing route (admin DEFAULT_ROUTES.AUTHED_ROUTE - admins land HERE, not on /accounts).
Organizations | Organizations | Yes | ⬜ | Not Started | Page | /user/organizations | User / Agent / Org / Tier | accessKey: organizations | modules/Organizations/containers | P0 | Declared landing route (user DEFAULT_ROUTES.CONTEXT_SELECTED_ROUTE).
Page | Page shell / layout | Yes | ⬜ | Not Started | Global chrome | n/a - mounted by AuthPage.js | All | n/a | modules/Page | P0 | Page header, breadcrumbs, side panel host.
Reviews | Reviews | Yes | ⬜ | Not Started | Page | /admin/account/reviews | Admin | accessKey: reviews_management ¦ app: pc_enable_3rd_party_review_mgmt | modules/Reviews/containers | P0
Reviews | Reviews | Yes | ⬜ | Not Started | Page | /user/account/reviews | User / Agent / Org / Tier | accessKey: reviews_management ¦ app: pc_enable_3rd_party_review_mgmt ¦ isForAgent: false | modules/Reviews/containers | P0 | Two intentional entries (agent vs non-agent). Latent bug: both share React key '/account/reviews' when isAgentLogin is true (AuthRouter.js:159).
Settings | Settings | Yes | ⬜ | Not Started | Page | /admin/account/settings | Admin | accessKey: settings | modules/Settings/containers | P0
Settings | Settings | Yes | ⬜ | Not Started | Page | /user/account/settings | User / Agent / Org / Tier | accessKey: settings | modules/Settings/containers | P0
UserManagement | UserDetails | Yes | ⬜ | Not Started | Page | /admin/individualprofessionals/manageusers | Admin | accessKey: user_management | modules/UserManagement/components/UserDetails | P0 | Declared landing route (admin DEFAULT_ROUTES.INDIVIDUAL_PROFESSIONALS_ROUTE).
AccountSettings | Account | No - dead | ⬜ | Excluded | Page | /admin/account | Admin | None (authenticated only) | modules/AccountSettings/containers | P1 | Renders the AccountSettings drawer container with no showAccountSetting prop - blank page.
AccountSettings | Account | No - dead | ⬜ | Excluded | Page | /user/account | User / Agent / Org / Tier | None (authenticated only) | modules/AccountSettings/containers | P1 | Renders the AccountSettings drawer container with no showAccountSetting prop - blank page.
Admins | AdminActivityFeed | Yes | ⬜ | Not Started | Page | /admin/activityfeed | Admin | accessKey: admins | modules/Admins/components/ActivityFeed/containers | P1
Admins | Admins | Yes | ⬜ | Not Started | Page | /admin/adminslist | Admin | accessKey: admins | modules/Admins/containers | P1
AppSettings | AppSettings | Yes | ⬜ | Not Started | Page | /admin/settings | Admin | accessKey: admin_settings | modules/AppSettings | P1
AppSettings | AssetManagement | Yes | ⬜ | Not Started | Page | /admin/settings/assetmanagement | Admin | accessKey: admin_settings | modules/AppSettings/components/AssetManagement | P1
AppSettings | BannerManagement | Yes | ⬜ | Not Started | Page | /admin/settings/banners | Admin | accessKey: admin_settings | modules/AppSettings/components/BannerManagement | P1
AppSettings | BannerManagement | Yes | ⬜ | Not Started | Page | /admin/settings/banners/edit_template | Admin | accessKey: admin_settings | modules/AppSettings/components/BannerManagement | P1
AppSettings | BannerManagement | Yes | ⬜ | Not Started | Page | /admin/settings/banners/impressions | Admin | accessKey: admin_settings | modules/AppSettings/components/BannerManagement | P1
AppSettings | CampaignTemplates | Yes | ⬜ | Not Started | Page | /admin/settings/campaigntemplates | Admin | accessKey: admin_settings | modules/AppSettings/components/CampaignTemplates | P1
AppSettings | TemplateEditor | No - other discipline | ⬜ | Excluded | Page | /admin/settings/campaigntemplates/templateseditor | Admin | accessKey: admin_settings | modules/AppSettings/components/TemplateEditor | P1 | Campaigns editor internals belong to the Campaigns discipline (deck slide 13). XMP ports the Campaigns list only.
AppSettings | EmailDeliveryDomain | Yes | ⬜ | Not Started | Page | /admin/settings/customfromemails-deliverydomains | Admin | accessKey: admin_settings | modules/AppSettings/components/EmailDeliveryDomain | P1
AppSettings | EngagementApp | Yes | ⬜ | Not Started | Page | /admin/settings/engagement | Admin | accessKey: admin_settings | modules/AppSettings/components/EngagementApp | P1
AppSettings | EmailServiceProvider | Yes | ⬜ | Not Started | Page | /admin/settings/engagement/emailserviceprovider | Admin | accessKey: admin_settings | modules/AppSettings/components/EngagementApp/components/EmailServiceProvider | P1
AppSettings | Senders | Yes | ⬜ | Not Started | Page | /admin/settings/engagement/senders | Admin | accessKey: admin_settings | modules/AppSettings/components/EngagementApp/components/Senders | P1
AppSettings | SMTPUsers | Yes | ⬜ | Not Started | Page | /admin/settings/engagement/smtpusers | Admin | accessKey: admin_settings | modules/AppSettings/components/EngagementApp/components/SMTPUsers | P1
AppSettings | Triggers | Yes | ⬜ | Not Started | Page | /admin/settings/engagement/triggers | Admin | accessKey: admin_settings | modules/AppSettings/components/EngagementApp/components/Triggers | P1
AppSettings | UnsubscribedDomains | Yes | ⬜ | Not Started | Page | /admin/settings/engagement/unsubscribeddomains | Admin | accessKey: admin_settings | modules/AppSettings/components/EngagementApp/components/UnsubscribedDomains | P1
AppSettings | PromoCodesManagment | Yes | ⬜ | Not Started | Page | /admin/settings/promocodesmanagement | Admin | accessKey: admin_settings | modules/AppSettings/components/PromoCodesManagement/containers | P1
AppSettings | UnsubscribedContacts | Yes | ⬜ | Not Started | Page | /admin/settings/unsubscriberequests | Admin | accessKey: admin_settings | modules/AppSettings/components/UnsubscribedContacts | P1
Auth | SignupClaimProfile | Yes | ⬜ | Not Started | Anonymous page | /user/claim-profile | User / Agent / Org / Tier | Public | modules/Auth/components/UserSignInSignUp/SignupClaimProfile | P1
Auth | ClaimProfileVerifyFromSwis | Yes | ⬜ | Not Started | Anonymous page | /user/claim_profile/:slug | User / Agent / Org / Tier | Public | modules/Auth/components/UserProfileSetup/ClaimProfile/components/ClaimProfileVerifyFromSwis | P1
Auth | CongratsPage | Yes | ⬜ | Not Started | Anonymous page | /user/claimprofile | User / Agent / Org / Tier | Public | modules/Auth/components/UserSignInSignUp/SignUp/ClaimFlow/components/VerificationMethod/partials/CongratsPage | P1
Auth | AccountConfirmation | Yes | ⬜ | Not Started | Page | /user/confirm-account | User / Agent / Org / Tier | None (authenticated only) | modules/Auth/components/UserSignInSignUp/ThirdPartySignup/AccountConfirmation | P1
Auth | ResetNewPassword | Yes | ⬜ | Not Started | Anonymous page | /user/new-password | User / Agent / Org / Tier | Public | modules/Auth/containers/ResetNewPasswordIndex | P1
Auth | OnboardingNewPassword | Yes | ⬜ | Not Started | Anonymous page | /user/onboarding-password | User / Agent / Org / Tier | Public | modules/Auth/containers/OnboardingNewPasswordIndex | P1
Auth | ResetPassword | Yes | ⬜ | Not Started | Anonymous page | /user/reset | User / Agent / Org / Tier | Public | modules/Auth/components/UserSignInSignUp/SignIn/ResetPassword | P1
Auth | NewSignupPage | Yes | ⬜ | Not Started | Anonymous page | /user/signup | User / Agent / Org / Tier | Public | modules/Auth/components/UserSignInSignUp/NewSignupPage | P1
Auth | SSOInputForm | Yes | ⬜ | Not Started | Anonymous page | /user/sso/signup | User / Agent / Org / Tier | Public | modules/Auth/components/UserSignInSignUp/EmailSignup/SSOInputForm | P1
Auth | VerifyEmail | Yes | ⬜ | Not Started | Verification page | /user/verify_email | User / Agent / Org / Tier | None (authenticated only) | modules/Auth/containers/VerifyEmailIndex | P1
Auth | VerifyEmail | Yes | ⬜ | Not Started | Verification page | /user/verify_manager_email | User / Agent / Org / Tier | None (authenticated only) | modules/Auth/containers/VerifyEmailIndex | P1
Auth | VerifyEmailWrapper | Yes | ⬜ | Not Started | Anonymous page | /user/verifyemail | User / Agent / Org / Tier | Public | modules/Auth/components/UserSignInSignUp/VerifyEmail | P1
Auth | ResetNewPassword | Yes | ⬜ | Not Started | Anonymous page | /xpa/new-password | XPA | Public | modules/Auth/containers/ResetNewPasswordIndex | P1
Auth | OnboardingNewPassword | Yes | ⬜ | Not Started | Anonymous page | /xpa/onboarding-password | XPA | Public | modules/Auth/containers/OnboardingNewPasswordIndex | P1
Auth | ResetPassword | Yes | ⬜ | Not Started | Anonymous page | /xpa/reset | XPA | Public | modules/Auth/containers/ResetPasswordIndex | P1
Bundles | Bundles | Yes | ⬜ | Not Started | Page | /admin/account/bundles | Admin | None (authenticated only) | modules/Bundles/containers | P1
Bundles | Bundles | Yes | ⬜ | Not Started | Page | /user/account/bundles | User / Agent / Org / Tier | None (authenticated only) | modules/Bundles/containers | P1
Campaigns | Campaigns | Yes | ⬜ | Not Started | Page | /admin/account/campaigns | Admin | accessKey: campaigns ¦ app: pc_enable_survey_campaign | modules/Campaigns/containers | P1 | Campaigns LIST only - navigational parity. Editor/settings/audience are slide 13's scope.
Campaigns | CampaignViewAllActivity | Yes | ⬜ | Not Started | Page | /admin/account/campaigns/activityfeeds | Admin | accessKey: campaigns | modules/Campaigns/containers/ViewAllActivity | P1
Campaigns | CampaignEditor | No - other discipline | ⬜ | Excluded | Page | /admin/account/campaigns/editor | Admin | accessKey: campaigns ¦ app: pc_enable_survey_campaign | modules/Campaigns/CampaignEditor | P1 | Campaigns editor internals belong to the Campaigns discipline (deck slide 13). XMP ports the Campaigns list only.
Campaigns | Campaigns | Yes | ⬜ | Not Started | Page | /user/account/campaigns | User / Agent / Org / Tier | accessKey: campaigns ¦ app: pc_enable_survey_campaign | modules/Campaigns/containers | P1 | Campaigns LIST only - navigational parity. Editor/settings/audience are slide 13's scope.
Campaigns | CampaignViewAllActivity | Yes | ⬜ | Not Started | Page | /user/account/campaigns/activityfeeds | User / Agent / Org / Tier | accessKey: campaigns | modules/Campaigns/containers/ViewAllActivity | P1
Campaigns | CampaignEditor | No - other discipline | ⬜ | Excluded | Page | /user/account/campaigns/editor | User / Agent / Org / Tier | accessKey: campaigns ¦ app: pc_enable_survey_campaign | modules/Campaigns/CampaignEditor | P1 | Campaigns editor internals belong to the Campaigns discipline (deck slide 13). XMP ports the Campaigns list only.
DataAndAnalysis | DataAndAnalysis | Yes | ⬜ | Not Started | Page | /admin/account/dataanalysis | Admin | accessKey: data_analysis | modules/DataAndAnalysis | P1
DataAndAnalysis | ReviewDetails | Yes | ⬜ | Not Started | Page | /admin/account/dataanalysis/reviewDetails | Admin | accessKey: data_analysis | modules/DataAndAnalysis/partials/ReviewDetails | P1
DataAndAnalysis | DataAndAnalysis | Yes | ⬜ | Not Started | Page | /user/account/dataanalysis | User / Agent / Org / Tier | accessKey: data_analysis | modules/DataAndAnalysis | P1
DataAndAnalysis | ReviewDetails | Yes | ⬜ | Not Started | Page | /user/account/dataanalysis/reviewDetails | User / Agent / Org / Tier | accessKey: data_analysis | modules/DataAndAnalysis/partials/ReviewDetails | P1
GlobalDrawer | Global drawer host | Yes | ⬜ | Not Started | Global chrome | n/a - mounted by AuthRouter.js:10 | All | n/a | modules/GlobalDrawer | P1 | Hosts app-wide drawers.
HierarchyDashboards | AdvancedAnalytics | Yes | ⬜ | Not Started | Page | /admin/account/analytics | Admin | accessKey: advanced_analytics | modules/HierarchyDashboards/components/partials/AdvancedAnalytics/containers | P1
HierarchyDashboards | MoxiAnalytics | Yes | ⬜ | Not Started | Page | /admin/account/moxi | Admin | accessKey: advanced_analytics | modules/HierarchyDashboards/components/partials/MoxiAnalytics/containers | P1
HierarchyDashboards | AdvancedAnalytics | Yes | ⬜ | Not Started | Page | /user/account/analytics | User / Agent / Org / Tier | accessKey: advanced_analytics | modules/HierarchyDashboards/components/partials/AdvancedAnalytics/containers | P1
HierarchyDashboards | MoxiAnalytics | Yes | ⬜ | Not Started | Page | /user/account/moxi | User / Agent / Org / Tier | accessKey: advanced_analytics | modules/HierarchyDashboards/components/partials/MoxiAnalytics/containers | P1
Integrations | Integrations | Yes | ⬜ | Not Started | Page | /user/account/integrations | User / Agent / Org / Tier | accessKey: integrations | modules/Integrations/containers | P1
LeaderBoard | LeaderBoardPage | Yes | ⬜ | Not Started | Page | /admin/account/leaderboard | Admin | accessKey: dashboard | modules/LeaderBoard/containers | P1
LeaderBoard | LeaderBoardPage | Yes | ⬜ | Not Started | Page | /user/account/leaderboard | User / Agent / Org / Tier | accessKey: dashboard | modules/LeaderBoard/containers | P1
Listing | DataIssues | Yes | ⬜ | Not Started | Page | /admin/account/Listing/dataissues | Admin | accessKey: listings ¦ app: pc_enable_listings | modules/Listing/submodules/DataIssues/containers | P1
Listing | ListingAuthorize | Yes | ⬜ | Not Started | Page | /admin/account/Listing/targetAuthorize | Admin | accessKey: listings ¦ app: pc_enable_listings | modules/Listing/submodules/Authorize/containers | P1
Listing | AllLocations | Yes | ⬜ | Not Started | Page | /admin/account/alllocations | Admin | accessKey: listings ¦ app: pc_enable_listings | modules/Listing/submodules/Locations/containers | P1
Listing | ListingCustomerDashboard | Yes | ⬜ | Not Started | Page | /admin/account/listing/dashboard | Admin | accessKey: listings ¦ app: pc_enable_listings | modules/Listing/submodules/CustomerListingDashboard/container | P1
Listing | FacebookAuthorize | Yes | ⬜ | Not Started | Page | /admin/account/listing/facebookauthorize | Admin | accessKey: listings ¦ app: pc_enable_listings | modules/Listing/submodules/FacebookAuth/containers | P1
Listing | GooglePosts | Yes | ⬜ | Not Started | Page | /admin/account/listing/googleposts | Admin | accessKey: listings ¦ app: pc_enable_listings | modules/Listing/submodules/GooglePosts/components/index.js | P1
Listing | LoadingPage | Yes | ⬜ | Not Started | Page | /admin/account/listing/loadingpage | Admin | app: pc_enable_listings | modules/Listing/submodules/AuthLoading/containers | P1
Listing | QuestionAndAnswer | Yes | ⬜ | Not Started | Page | /admin/account/listing/questionandanswer | Admin | accessKey: listings ¦ app: pc_enable_listings | modules/Listing/submodules/QuestionAndAnswer/containers | P1
Listing | ListingTargetSites | Yes | ⬜ | Not Started | Page | /admin/account/listing/targetsites | Admin | accessKey: listings ¦ app: pc_enable_listings | modules/Listing/submodules/ListingTargetSites/containers | P1
Listing | ListingViewAllActivity | Yes | ⬜ | Not Started | Page | /admin/account/listing/viewallactivity | Admin | accessKey: listings ¦ app: pc_enable_listings | modules/Listing/submodules/ViewAllActivity/container | P1
Listing | DataIssues | Yes | ⬜ | Not Started | Page | /user/account/Listing/dataissues | User / Agent / Org / Tier | accessKey: listings ¦ app: pc_enable_listings | modules/Listing/submodules/DataIssues/containers | P1
Listing | ListingAuthorize | Yes | ⬜ | Not Started | Page | /user/account/Listing/targetAuthorize | User / Agent / Org / Tier | accessKey: listings ¦ app: pc_enable_listings | modules/Listing/submodules/Authorize/containers | P1
Listing | AllLocations | Yes | ⬜ | Not Started | Page | /user/account/alllocations | User / Agent / Org / Tier | accessKey: listings ¦ app: pc_enable_listings | modules/Listing/submodules/Locations/containers | P1
Listing | FacebookAuthorize | Yes | ⬜ | Not Started | Page | /user/account/listing/facebookauthorize | User / Agent / Org / Tier | accessKey: listings ¦ app: pc_enable_listings | modules/Listing/submodules/FacebookAuth/containers | P1
Listing | GooglePosts | Yes | ⬜ | Not Started | Page | /user/account/listing/googleposts | User / Agent / Org / Tier | accessKey: listings ¦ app: pc_enable_listings | modules/Listing/submodules/GooglePosts/components/index.js | P1
Listing | LoadingPage | Yes | ⬜ | Not Started | Page | /user/account/listing/loadingpage | User / Agent / Org / Tier | app: pc_enable_listings | modules/Listing/submodules/AuthLoading/containers | P1
Listing | QuestionAndAnswer | Yes | ⬜ | Not Started | Page | /user/account/listing/questionandanswer | User / Agent / Org / Tier | accessKey: listings ¦ app: pc_enable_listings | modules/Listing/submodules/QuestionAndAnswer/containers | P1
Listing | ListingTargetSites | Yes | ⬜ | Not Started | Page | /user/account/listing/targetsites | User / Agent / Org / Tier | accessKey: listings ¦ app: pc_enable_listings | modules/Listing/submodules/ListingTargetSites/containers | P1
Listing | ListingViewAllActivity | Yes | ⬜ | Not Started | Page | /user/account/listing/viewallactivity | User / Agent / Org / Tier | accessKey: listings ¦ app: pc_enable_listings | modules/Listing/submodules/ViewAllActivity/container | P1
Listings | UserListings | Yes | ⬜ | Not Started | Page | /admin/locations | Admin | accessKey: listings ¦ app: pc_enable_listings | modules/Listings/UserListings/main | P1
Listings | UserListings | Yes | ⬜ | Not Started | Page | /user/locations | User / Agent / Org / Tier | accessKey: listings ¦ app: pc_enable_listings ¦ feature: PERSONA_FEATURES?.LISTINGS | modules/Listings/UserListings/main | P1
Listings | UserListings | Yes | ⬜ | Not Started | Page | /user/locations/posts | User / Agent / Org / Tier | accessKey: listings ¦ app: pc_enable_listings ¦ feature: PERSONA_FEATURES?.LISTINGS | modules/Listings/UserListings/main | P1
Mismatches | Mismatches | Yes | ⬜ | Not Started | Page | /admin/account/unprocessed | Admin | accessKey: unprocessed | modules/Mismatches/containers | P1
Mismatches | Mismatches | Yes | ⬜ | Not Started | Page | /user/account/unprocessed | User / Agent / Org / Tier | accessKey: unprocessed | modules/Mismatches/containers | P1
Notifications | Notifications | Yes | ⬜ | Not Started | Page | /admin/account/notifications | Admin | accessKey: accounts | modules/Notifications | P1
Notifications | Notifications | Yes | ⬜ | Not Started | Page | /admin/notifications | Admin | accessKey: accounts | modules/Notifications | P1
Notifications | Notifications | Yes | ⬜ | Not Started | Page | /user/account/notifications | User / Agent / Org / Tier | accessKey: dashboard | modules/Notifications | P1
Notifications | Notifications | Yes | ⬜ | Not Started | Page | /user/notifications | User / Agent / Org / Tier | accessKey: dashboard | modules/Notifications | P1
OrganizationSettings | OrganizationSettings | Yes | ⬜ | Not Started | Page | /admin/organizations/settings | Admin | accessKey: organization_settings | modules/OrganizationSettings/containers | P1
OrganizationSettings | OrganizationSettings | Yes | ⬜ | Not Started | Page | /user/organizations/settings | User / Agent / Org / Tier | accessKey: organization_settings | modules/OrganizationSettings/containers | P1
Organizations | OrganizationDetails | Yes | ⬜ | Not Started | Page | /admin/organizations/accounts | Admin | accessKey: organization_accounts | modules/Organizations/containers/OrganizationDetails | P1
Organizations | OrganizationUsers | Yes | ⬜ | Not Started | Page | /admin/organizations/users | Admin | accessKey: organization_users | modules/Organizations/containers/OrganizationUsers | P1
Organizations | OrganizationDetails | Yes | ⬜ | Not Started | Page | /user/organizations/accounts | User / Agent / Org / Tier | accessKey: organization_accounts | modules/Organizations/containers/OrganizationDetails | P1
Organizations | OrganizationUsers | Yes | ⬜ | Not Started | Page | /user/organizations/users | User / Agent / Org / Tier | accessKey: organization_users | modules/Organizations/containers/OrganizationUsers | P1
Profile | Profile | Yes | ⬜ | Not Started | Page | /admin/account/hierarchy/preview | Admin | accessKey: hierarchy | modules/Profile/containers | P1
Profile | Profile | No - duplicate | ⬜ | Excluded | Page | /admin/account/hierarchy/preview | Admin | accessKey: hierarchy | modules/Profile/containers | P1 | Identical duplicate of the earlier entry; unreachable because <Switch> renders the first match.
Profile | Profile | Yes | ⬜ | Not Started | Page | /admin/account/reviews/profile | Admin | accessKey: hierarchy | modules/Profile/containers | P1
Profile | Profile | Yes | ⬜ | Not Started | Page | /user/account/hierarchy/preview | User / Agent / Org / Tier | accessKey: profile,hierarchy | modules/Profile/containers | P1
Profile | Profile | No - duplicate | ⬜ | Excluded | Page | /user/account/hierarchy/preview | User / Agent / Org / Tier | accessKey: profile,hierarchy | modules/Profile/containers | P1 | Identical duplicate of the earlier entry; unreachable because <Switch> renders the first match.
Profile | Profile | Yes | ⬜ | Not Started | Page | /user/account/reviews/profile | User / Agent / Org / Tier | accessKey: profile,hierarchy | modules/Profile/containers | P1
ProfileEnhancement | ProfileEnhancement | Yes | ⬜ | Not Started | Page | /user/account/upgrades | User / Agent / Org / Tier | accessKey: profile,hierarchy | modules/ProfileEnhancement/containers | P1
ProfileEnhancement | ProfileEnhancement | Yes | ⬜ | Not Started | Page | /user/account/upgrades/manage-subscriptions | User / Agent / Org / Tier | accessKey: profile_enhancement | modules/ProfileEnhancement/containers | P1
ProfileEnhancement | ProfileEnhancement | Yes | ⬜ | Not Started | Page | /user/account/upgrades/packages | User / Agent / Org / Tier | accessKey: profile_enhancement | modules/ProfileEnhancement/containers | P1
Reports | Reports | Yes | ⬜ | Not Started | Page | /admin/account/reports | Admin | accessKey: account_reports | modules/Reports/containers | P1
Reports | ReportViewAllActivity | Yes | ⬜ | Not Started | Page | /admin/account/reports/viewallactivity | Admin | accessKey: account_reports | modules/Reports/containers/ViewAllActivity | P1
Reports | Reports | Yes | ⬜ | Not Started | Page | /admin/generatereports | Admin | accessKey: reports | modules/Reports/containers | P1
Reports | ReportViewAllActivity | Yes | ⬜ | Not Started | Page | /admin/generatereports/viewallactivity | Admin | accessKey: reports | modules/Reports/containers/ViewAllActivity | P1
Reports | Reports | Yes | ⬜ | Not Started | Page | /admin/organizations/generatereports | Admin | accessKey: organization_report | modules/Reports/containers | P1
Reports | ReportViewAllActivity | Yes | ⬜ | Not Started | Page | /admin/organizations/generatereports/viewallactivity | Admin | accessKey: organization_report | modules/Reports/containers/ViewAllActivity | P1
Reports | Reports | Yes | ⬜ | Not Started | Page | /user/account/reports | User / Agent / Org / Tier | accessKey: account_reports | modules/Reports/containers | P1
Reports | ReportViewAllActivity | Yes | ⬜ | Not Started | Page | /user/account/reports/viewallactivity | User / Agent / Org / Tier | accessKey: account_reports | modules/Reports/containers/ViewAllActivity | P1
Reports | Reports | Yes | ⬜ | Not Started | Page | /user/generatereports | User / Agent / Org / Tier | accessKey: reports | modules/Reports/containers | P1
Reports | ReportViewAllActivity | Yes | ⬜ | Not Started | Page | /user/generatereports/viewallactivity | User / Agent / Org / Tier | accessKey: reports | modules/Reports/containers/ViewAllActivity | P1
Reports | Reports | Yes | ⬜ | Not Started | Page | /user/organizations/generatereports | User / Agent / Org / Tier | accessKey: organization_report | modules/Reports/containers | P1
Reports | ReportViewAllActivity | Yes | ⬜ | Not Started | Page | /user/organizations/generatereports/viewallactivity | User / Agent / Org / Tier | accessKey: organization_report | modules/Reports/containers/ViewAllActivity | P1
RequestReview | RequestTable | Yes | ⬜ | Not Started | Page | /user/account/manage-review-requests | User / Agent / Org / Tier | accessKey: reviews_management | modules/RequestReview/ManageReviewRequests/RequestTable | P1
ReviewWidget | ReviewWidget | Yes | ⬜ | Not Started | Page | /admin/account/widgets | Admin | accessKey: widgets | modules/ReviewWidget/containers | P1
ReviewWidget | AgentWidget | Yes | ⬜ | Not Started | Page | /admin/account/widgets/agentwidget | Admin | None (authenticated only) | modules/ReviewWidget/Submodules/AgentWidget/containers | P1
ReviewWidget | ReviewsWidgets | Yes | ⬜ | Not Started | Page | /admin/account/widgets/reviewwidget | Admin | accessKey: widgets | modules/ReviewWidget/Submodules/ReviewWidgets/containers | P1
ReviewWidget | ReviewWidget | Yes | ⬜ | Not Started | Page | /user/account/widgets | User / Agent / Org / Tier | accessKey: widgets | modules/ReviewWidget/containers | P1
ReviewWidget | ReviewsWidgets | Yes | ⬜ | Not Started | Page | /user/account/widgets/reviewwidget | User / Agent / Org / Tier | accessKey: widgets | modules/ReviewWidget/Submodules/ReviewWidgets/containers | P1
Reviews | ReviewsActivityFeed | Yes | ⬜ | Not Started | Page | /admin/account/reviews/activityfeed | Admin | None (authenticated only) | modules/Reviews/components/ActivityFeed/containers | P1
Reviews | ReviewsActivityFeed | Yes | ⬜ | Not Started | Page | /user/account/reviews/activityfeed | User / Agent / Org / Tier | None (authenticated only) | modules/Reviews/components/ActivityFeed/containers | P1
Settings | IntegrationsViewAllActivityFeedSettings | Yes | ⬜ | Not Started | Page | /admin/account/integrationsettings/activityfeeds | Admin | accessKey: settings | modules/Settings/components/Integrations/Components/IntegrationsViewAllActivity | P1
Settings | ViewAllActivityFeedSettings | Yes | ⬜ | Not Started | Page | /admin/account/settings/activityfeeds | Admin | accessKey: settings | modules/Settings/components/IngestionSettings/ViewAllActivity | P1
Settings | AccountAssetManagement | Yes | ⬜ | Not Started | Page | /admin/account/settings/assetmanagement | Admin | accessKey: settings | modules/Settings/components/AccountAssetManagement | P1
Settings | AutopostSettings | Yes | ⬜ | Not Started | Page | /admin/account/settings/autopostsettings | Admin | accessKey: settings | modules/Settings/components/AutopostSettings | P1
Settings | AccountCampaignSettings | Yes | ⬜ | Not Started | Page | /admin/account/settings/campaignsettings | Admin | accessKey: settings | modules/Settings/components/AccountCampaignSettings | P1
Settings | EmailSetup | Yes | ⬜ | Not Started | Page | /admin/account/settings/emailsetup | Admin | accessKey: settings | modules/Settings/components/EmailSetup/containers | P1
Settings | IngestionSettings | Yes | ⬜ | Not Started | Page | /admin/account/settings/ingestionsettings | Admin | accessKey: settings | modules/Settings/containers/IngestionSettings | P1
Settings | IngestionSettings | Yes | ⬜ | Not Started | Page | /admin/account/settings/manageConnection | Admin | accessKey: settings | modules/Settings/containers/IngestionSettings | P1
Settings | IntegrationsViewAllActivityFeedSettings | Yes | ⬜ | Not Started | Page | /user/account/integrationsettings/activityfeeds | User / Agent / Org / Tier | accessKey: settings | modules/Settings/components/Integrations/Components/IntegrationsViewAllActivity | P1
Settings | ViewAllActivityFeedSettings | Yes | ⬜ | Not Started | Page | /user/account/settings/activityfeeds | User / Agent / Org / Tier | accessKey: settings | modules/Settings/components/IngestionSettings/ViewAllActivity | P1
Settings | AssetManagement | Yes | ⬜ | Not Started | Page | /user/account/settings/assetmanagement | User / Agent / Org / Tier | accessKey: settings | modules/Settings/components/AccountAssetManagement | P1
Settings | AutopostSettings | Yes | ⬜ | Not Started | Page | /user/account/settings/autopostsettings | User / Agent / Org / Tier | accessKey: settings | modules/Settings/components/AutopostSettings | P1
Settings | AccountCampaignSettings | Yes | ⬜ | Not Started | Page | /user/account/settings/campaignsettings | User / Agent / Org / Tier | accessKey: settings | modules/Settings/components/AccountCampaignSettings | P1
Settings | EmailSetup | Yes | ⬜ | Not Started | Page | /user/account/settings/emailsetup | User / Agent / Org / Tier | accessKey: settings | modules/Settings/components/EmailSetup/containers | P1
Settings | IngestionSettings | Yes | ⬜ | Not Started | Page | /user/account/settings/ingestionsettings | User / Agent / Org / Tier | accessKey: settings | modules/Settings/containers/IngestionSettings | P1
Transactions | Transactions | Yes | ⬜ | Not Started | Page | /admin/account/transaction | Admin | accessKey: transaction_monitor | modules/Transactions/containers | P1
Transactions | Transactions | Yes | ⬜ | Not Started | Page | /admin/account/transactions | Admin | None (authenticated only) | modules/Transactions/containers | P1
Transactions | Transactions | Yes | ⬜ | Not Started | Page | /admin/transaction | Admin | accessKey: transaction_monitor | modules/Transactions/containers | P1
Transactions | Transactions | Yes | ⬜ | Not Started | Page | /user/account/transaction | User / Agent / Org / Tier | accessKey: transaction_monitor | modules/Transactions/containers | P1
Transactions | Transactions | Yes | ⬜ | Not Started | Page | /user/account/transactions | User / Agent / Org / Tier | None (authenticated only) | modules/Transactions/containers | P1
Transactions | Transactions | Yes | ⬜ | Not Started | Page | /user/organizations/transaction | User / Agent / Org / Tier | accessKey: transaction_monitor | modules/Transactions/containers | P1
Transactions | Transactions | Yes | ⬜ | Not Started | Page | /user/transaction | User / Agent / Org / Tier | accessKey: transaction_monitor | modules/Transactions/containers | P1
UserManagement | ChatbotHistory | Yes | ⬜ | Not Started | Page | /admin/chathistory | Admin | accessKey: user_management | modules/UserManagement/components/ChatBotHistory | P1
UserManagement | UserManagement | Yes | ⬜ | Not Started | Page | /admin/individualprofessionals | Admin | accessKey: user_management | modules/UserManagement/containers | P1
UserManagement | EmailVerification | Yes | ⬜ | Not Started | Page | /admin/individualprofessionals/emailverification | Admin | accessKey: user_management | modules/UserManagement/components/EmailVerification/container | P1
(routes infra: PageNotFound) | PageNotFound | Yes | ⬜ | Not Started | Page | /admin* | Admin | None (authenticated only) | ../components/PageNotFound | P2
(routes infra: PageNotFound) | PageNotFound | Yes | ⬜ | Not Started | Page | /admin/pagenotfound | Admin | None (authenticated only) | ../components/PageNotFound | P2
(routes infra: PageNotFound) | PageNotFound | Yes | ⬜ | Not Started | Page | /user* | User / Agent / Org / Tier | None (authenticated only) | ../components/PageNotFound | P2
(routes infra: PageNotFound) | PageNotFound | Yes | ⬜ | Not Started | Page | /user/pagenotfound | User / Agent / Org / Tier | None (authenticated only) | ../components/PageNotFound | P2
(shared components) | UnsubscribeEmail | Yes | ⬜ | Not Started | Anonymous page | /user/unsubscribe | User / Agent / Org / Tier | Public | components/UnsubscribeEmail | P2
(shared components) | EmailUnsubscription | Yes | ⬜ | Not Started | Anonymous page | /user/unsubscribe_email | User / Agent / Org / Tier | Public | components/EmailUnsubscription | P2
AIVisibility | AIVisibility | Yes | ⬜ | Not Started | Page | /user/account/aivisibility | User / Agent / Org / Tier | accessKey: ai_visibility | modules/AIVisibility | P2
AbusiveReviews | AbusiveReview | Yes | ⬜ | Not Started | Page | /admin/abusivereviews | Admin | accessKey: abusive_review_management | modules/AbusiveReviews/containers | P2
AdminGroups | AdminGroups | Yes | ⬜ | Not Started | Page | /admin/groups | Admin | accessKey: admin_groups | modules/AdminGroups/containers | P2
AgentDashboard | AgentDashboard | Yes | ⬜ | Not Started | Page | /user/account/user-dashboard/onboarding/:step | User / Agent / Org / Tier | accessKey: dashboard | modules/AgentDashboard/containers | P2
AgentSettings | AgentSettings | Yes | ⬜ | Not Started | Page | /user/account/hierarchy/user-settings | User / Agent / Org / Tier | accessKey: profile | modules/AgentSettings/containers | P2
Auth | oktaLoginIndex | Yes | ⬜ | Not Started | Anonymous page | /user/One-login | User / Agent / Org / Tier | Public | modules/Auth/containers/OktaConnectionLoginIndex | P2
Auth | ActiveUserSignup | Yes | ⬜ | Not Started | Anonymous page | /user/active-user | User / Agent / Org / Tier | Public | modules/Auth/components/UserSignInSignUp/ConfirmationScreens/ActiveUserSignup | P2
Auth | CustomerExperiencePageinAws | Yes | ⬜ | Not Started | Anonymous page | /user/customer-experience | User / Agent / Org / Tier | Public | modules/Auth/containers/CustomerExperienceAwsIndex | P2
Auth | CustomerExperienceVerifiedPageinAws | Yes | ⬜ | Not Started | Anonymous page | /user/customer-experience-success | User / Agent / Org / Tier | Public | modules/Auth/containers/VerifiedUserForAwsCustomerExperience | P2
Auth | UserAccountDisabled | Yes | ⬜ | Not Started | Anonymous page | /user/deactivated-account | User / Agent / Org / Tier | Public | modules/Auth/components/UserAccountDisabled | P2
Auth | EmailVerified | Yes | ⬜ | Not Started | Anonymous page | /user/email-verified | User / Agent / Org / Tier | Public | modules/Auth/components/UserSignInSignUp/EmailVerified | P2
Auth | UserSignUp | Yes | ⬜ | Not Started | Anonymous page | /user/free-seo-audit | User / Agent / Org / Tier | Public | modules/Auth/components/UserSignInSignUp/SignUp/index.js | P2
Auth | LinkExpired | Yes | ⬜ | Not Started | Anonymous page | /user/magic-link-expired | User / Agent / Org / Tier | Public | modules/Auth/components/UserSignInSignUp/SignupClaimProfile/LinkExpired/LinkExpired | P2
Auth | oktaLoginIndex | Yes | ⬜ | Not Started | Anonymous page | /user/okta-login | User / Agent / Org / Tier | Public | modules/Auth/containers/OktaConnectionLoginIndex | P2
Auth | PolicyConsent | Yes | ⬜ | Not Started | Anonymous page | /user/policy_consent | User / Agent / Org / Tier | Public | modules/Auth/components/TermsAndConditionsAgreement/policyConsent/index.js | P2
Auth | TermsAndConditionsAgreement | Yes | ⬜ | Not Started | Anonymous page | /user/terms-and-conditions-agreement | User / Agent / Org / Tier | Public | modules/Auth/components/TermsAndConditionsAgreement | P2
Auth | UserAccountUnverified | Yes | ⬜ | Not Started | Anonymous page | /user/unverified-account | User / Agent / Org / Tier | Public | modules/Auth/components/UserAccountUnverified | P2
Auth | RequestVerificationMail | Yes | ⬜ | Not Started | Anonymous page | /user/verification-mail | User / Agent / Org / Tier | Public | modules/Auth/containers/RequestVerificationMailIndex | P2
Auth | UserVerificationMail | Yes | ⬜ | Not Started | Anonymous page | /user/verificationmail-sent | User / Agent / Org / Tier | Public | modules/Auth/components/UserVerificationMail | P2
Campaigns | CampaignViewAllActivity | No - other discipline | ⬜ | Excluded | Page | /admin/account/campaigns/editor/activityfeeds | Admin | accessKey: campaigns | modules/Campaigns/containers/ViewAllActivity | P2 | Campaigns editor internals belong to the Campaigns discipline (deck slide 13). XMP ports the Campaigns list only.
Campaigns | CampaignSettings | No - other discipline | ⬜ | Excluded | Page | /admin/account/campaigns/editor/settings | Admin | accessKey: campaigns ¦ app: pc_enable_survey_campaign | modules/Campaigns/CampaignEditor/components/CampaignSettings | P2 | Campaigns editor internals belong to the Campaigns discipline (deck slide 13). XMP ports the Campaigns list only.
Campaigns | Versions | No - other discipline | ⬜ | Excluded | Page | /admin/account/campaigns/editor/versions | Admin | accessKey: campaigns ¦ app: pc_enable_survey_campaign | modules/Campaigns/CampaignEditor/components/Versions | P2 | Campaigns editor internals belong to the Campaigns discipline (deck slide 13). XMP ports the Campaigns list only.
Campaigns | CampaignSettings | No - other discipline | ⬜ | Excluded | Page | /admin/settings/campaigntemplates/templateseditor/settings | Admin | accessKey: admin_settings | modules/Campaigns/CampaignEditor/components/CampaignSettings | P2 | Campaigns editor internals belong to the Campaigns discipline (deck slide 13). XMP ports the Campaigns list only.
Campaigns | CampaignViewAllActivity | No - other discipline | ⬜ | Excluded | Page | /user/account/campaigns/editor/activityfeeds | User / Agent / Org / Tier | accessKey: campaigns | modules/Campaigns/containers/ViewAllActivity | P2 | Campaigns editor internals belong to the Campaigns discipline (deck slide 13). XMP ports the Campaigns list only.
Campaigns | CampaignSettings | No - other discipline | ⬜ | Excluded | Page | /user/account/campaigns/editor/settings | User / Agent / Org / Tier | accessKey: campaigns ¦ app: pc_enable_survey_campaign | modules/Campaigns/CampaignEditor/components/CampaignSettings | P2 | Campaigns editor internals belong to the Campaigns discipline (deck slide 13). XMP ports the Campaigns list only.
Campaigns | Versions | No - other discipline | ⬜ | Excluded | Page | /user/account/campaigns/editor/versions | User / Agent / Org / Tier | accessKey: campaigns ¦ app: pc_enable_survey_campaign | modules/Campaigns/CampaignEditor/components/Versions | P2 | Campaigns editor internals belong to the Campaigns discipline (deck slide 13). XMP ports the Campaigns list only.
ChatBot | Support chatbot widget | Yes | ⬜ | Not Started | Overlay | n/a - 4 importers | All | n/a | modules/ChatBot | P2 | Floating widget mounted from Page footer.
IncompleteSurvey | IncompleteSurvey | Yes | ⬜ | Not Started | Page | /admin/account/expiredsurvey | Admin | accessKey: expired_survey | modules/IncompleteSurvey | P2
IncompleteSurvey | IncompleteSurvey | Yes | ⬜ | Not Started | Page | /admin/account/incompletesurvey | Admin | accessKey: incomplete_survey | modules/IncompleteSurvey | P2
IncompleteSurvey | IncompleteSurvey | No - dead | ⬜ | Excluded | Page | /admin/account/incompletesurvey?campaignId | Admin | accessKey: incomplete_survey | modules/IncompleteSurvey | P2 | Query string inside routePath - React Router v5 matches pathname only, so this can never match.
IncompleteSurvey | IncompleteSurvey | Yes | ⬜ | Not Started | Page | /admin/account/unsubscribedTransactions | Admin | accessKey: unsubscribed_transactions | modules/IncompleteSurvey | P2
IncompleteSurvey | IncompleteSurvey | Yes | ⬜ | Not Started | Page | /user/account/expiredsurvey | User / Agent / Org / Tier | accessKey: expired_survey | modules/IncompleteSurvey | P2
IncompleteSurvey | IncompleteSurvey | Yes | ⬜ | Not Started | Page | /user/account/incompletesurvey | User / Agent / Org / Tier | accessKey: incomplete_survey | modules/IncompleteSurvey | P2
IncompleteSurvey | IncompleteSurvey | No - dead | ⬜ | Excluded | Page | /user/account/incompletesurvey?campaignId | User / Agent / Org / Tier | accessKey: incomplete_survey | modules/IncompleteSurvey | P2 | Query string inside routePath - React Router v5 matches pathname only, so this can never match.
IncompleteSurvey | IncompleteSurvey | Yes | ⬜ | Not Started | Page | /user/account/unsubscribedTransactions | User / Agent / Org / Tier | accessKey: unsubscribed_transactions | modules/IncompleteSurvey | P2
Insights | Insights | Yes | ⬜ | Not Started | Page | /user/account/insights | User / Agent / Org / Tier | accessKey: website_insights ¦ feature: PERSONA_FEATURES?.INSIGHTS | modules/Insights/Main | P2
LearningCenter | LearningCenter | Yes | ⬜ | Not Started | Page | /admin/account/learning-center | Admin | accessKey: learning_center | modules/LearningCenter | P2
LearningCenter | LearningCenter | Yes | ⬜ | Not Started | Page | /user/account/learning-center | User / Agent / Org / Tier | accessKey: learning_center | modules/LearningCenter | P2
NoConnectionFound | NoConnectionFound | Yes | ⬜ | Not Started | Page | /admin/account/noconnectionfound | Admin | accessKey: hierarchy | modules/NoConnectionFound | P2
NoConnectionFound | NoConnectionFound | Yes | ⬜ | Not Started | Page | /user/account/noconnectionfound | User / Agent / Org / Tier | accessKey: profile,hierarchy | modules/NoConnectionFound | P2
OnboardingGroupDashboard | OnboardingDashboard | Yes | ⬜ | Not Started | Page | /admin/onboardinggroupdashboard | Admin | accessKey: onboarding_group_dashboard | modules/OnboardingGroupDashboard/containers | P2
OnboardingGroupDashboard | ViewAllActivity | Yes | ⬜ | Not Started | Page | /admin/onboardinggroupdashboard/activityfeed | Admin | accessKey: onboarding_group_dashboard | modules/OnboardingGroupDashboard/containers/ViewAllActivity | P2
ProductGuide | Product tour overlays | Yes | ⬜ | Not Started | Overlay | n/a - 45 importers | All | n/a | modules/ProductGuide | P2 | Cross-cutting overlay; decide whether the port keeps tours.
Profile | Profile | Yes | ⬜ | Not Started | Page | /admin/account/campaigns/reviews/profile | Admin | accessKey: hierarchy | modules/Profile/containers | P2
Profile | Profile | Yes | ⬜ | Not Started | Page | /user/account/campaigns/reviews/profile | User / Agent / Org / Tier | accessKey: profile,hierarchy | modules/Profile/containers | P2
ProfileEnhancement | ProfileEnhancement | Yes | ⬜ | Not Started | Page | /user/account/upgrades/manage-subscriptions/cancel | User / Agent / Org / Tier | accessKey: profile_enhancement | modules/ProfileEnhancement/containers | P2
ProfileEnhancement | ProfileEnhancement | Yes | ⬜ | Not Started | Page | /user/account/upgrades/manage-subscriptions/checkout | User / Agent / Org / Tier | accessKey: profile_enhancement | modules/ProfileEnhancement/containers | P2
ProfileEnhancement | ProfileEnhancement | Yes | ⬜ | Not Started | Page | /user/account/upgrades/manage-subscriptions/payment | User / Agent / Org / Tier | accessKey: profile_enhancement | modules/ProfileEnhancement/containers | P2
ProfileEnhancement | ProfileEnhancement | Yes | ⬜ | Not Started | Page | /user/account/upgrades/packages/checkout | User / Agent / Org / Tier | accessKey: profile_enhancement | modules/ProfileEnhancement/containers | P2
ProfileEnhancement | ProfileEnhancement | Yes | ⬜ | Not Started | Page | /user/account/upgrades/packages/payment | User / Agent / Org / Tier | accessKey: profile_enhancement | modules/ProfileEnhancement/containers | P2
PromotePartners | PromotePartners | Yes | ⬜ | Not Started | Page | /user/account/promote-partners | User / Agent / Org / Tier | accessKey: pin_partner_profiles ¦ feature: PERSONA_FEATURES?.PIN_PARTNERS | modules/PromotePartners/components/main | P2
Referrals | Referrals | Yes | ⬜ | Not Started | Page | /user/account/referrals | User / Agent / Org / Tier | accessKey: referrals ¦ feature: PERSONA_FEATURES?.REFERRALS | modules/Referrals/containers | P2
Settings | AccountAssetManagement | No - other discipline | ⬜ | Excluded | Page | /admin/account/campaigns/editor/campaignassets | Admin | accessKey: campaigns | modules/Settings/components/AccountAssetManagement | P2 | Campaigns editor internals belong to the Campaigns discipline (deck slide 13). XMP ports the Campaigns list only.
Settings | CampaignQRCode | No - other discipline | ⬜ | Excluded | Page | /admin/account/campaigns/editor/qrcode | Admin | accessKey: campaigns ¦ app: pc_enable_survey_campaign | modules/Settings/components/AccountCampaignSettings/features/CampaignQRCode | P2 | Campaigns editor internals belong to the Campaigns discipline (deck slide 13). XMP ports the Campaigns list only.
Settings | CampaignsQRCodeExport | No - other discipline | ⬜ | Excluded | Page | /admin/account/campaigns/editor/qrcode/exportdetails | Admin | accessKey: campaigns ¦ app: pc_enable_survey_campaign | modules/Settings/components/AccountCampaignSettings/features/CampaignQRCode/Drawer/partials/CampaignQRCodeExport | P2 | Campaigns editor internals belong to the Campaigns discipline (deck slide 13). XMP ports the Campaigns list only.
Settings | AutopostSettingsDetail | Yes | ⬜ | Not Started | Page | /admin/account/settings/autopostsettings/:platform | Admin | accessKey: settings | modules/Settings/components/AutopostSettings/AutopostSettingsDetail | P2
Settings | CreateAutopostTemplate | Yes | ⬜ | Not Started | Page | /admin/account/settings/autopostsettings/:platform/create-template | Admin | accessKey: settings | modules/Settings/components/AutopostSettings/CreateAutopostTemplate | P2
Settings | CampaignAccessControl | Yes | ⬜ | Not Started | Page | /admin/account/settings/campaignsettings/accesscontrol | Admin | accessKey: settings | modules/Settings/components/AccountCampaignSettings/features/CampaignAccessControl | P2
Settings | CampaignUserAccess | Yes | ⬜ | Not Started | Page | /admin/account/settings/campaignsettings/accesscontrol/manageusers | Admin | accessKey: settings | modules/Settings/components/AccountCampaignSettings/features/CampaignAccessControl/components/CampaignUserAccess | P2
Settings | CampaignQRCode | Yes | ⬜ | Not Started | Page | /admin/account/settings/campaignsettings/qrcode | Admin | accessKey: settings | modules/Settings/components/AccountCampaignSettings/features/CampaignQRCode | P2
Settings | CampaignsQRCodeExport | Yes | ⬜ | Not Started | Page | /admin/account/settings/campaignsettings/qrcode/exportdetails | Admin | accessKey: settings | modules/Settings/components/AccountCampaignSettings/features/CampaignQRCode/Drawer/partials/CampaignQRCodeExport | P2
Settings | AssetManagement | No - other discipline | ⬜ | Excluded | Page | /user/account/campaigns/editor/campaignassets | User / Agent / Org / Tier | accessKey: campaigns | modules/Settings/components/AccountAssetManagement | P2 | Campaigns editor internals belong to the Campaigns discipline (deck slide 13). XMP ports the Campaigns list only.
Settings | CampaignQRCode | No - other discipline | ⬜ | Excluded | Page | /user/account/campaigns/editor/qrcode | User / Agent / Org / Tier | accessKey: campaigns ¦ app: pc_enable_survey_campaign | modules/Settings/components/AccountCampaignSettings/features/CampaignQRCode | P2 | Campaigns editor internals belong to the Campaigns discipline (deck slide 13). XMP ports the Campaigns list only.
Settings | CampaignsQRCodeExport | No - other discipline | ⬜ | Excluded | Page | /user/account/campaigns/editor/qrcode/exportdetails | User / Agent / Org / Tier | accessKey: campaigns ¦ app: pc_enable_survey_campaign | modules/Settings/components/AccountCampaignSettings/features/CampaignQRCode/Drawer/partials/CampaignQRCodeExport | P2 | Campaigns editor internals belong to the Campaigns discipline (deck slide 13). XMP ports the Campaigns list only.
Settings | AutopostSettingsDetail | Yes | ⬜ | Not Started | Page | /user/account/settings/autopostsettings/:platform | User / Agent / Org / Tier | accessKey: settings | modules/Settings/components/AutopostSettings/AutopostSettingsDetail | P2
Settings | CreateAutopostTemplate | Yes | ⬜ | Not Started | Page | /user/account/settings/autopostsettings/:platform/create-template | User / Agent / Org / Tier | accessKey: settings | modules/Settings/components/AutopostSettings/CreateAutopostTemplate | P2
Settings | CampaignAccessControl | Yes | ⬜ | Not Started | Page | /user/account/settings/campaignsettings/accesscontrol | User / Agent / Org / Tier | accessKey: settings | modules/Settings/components/AccountCampaignSettings/features/CampaignAccessControl | P2
Settings | CampaignUserAccess | Yes | ⬜ | Not Started | Page | /user/account/settings/campaignsettings/accesscontrol/manageusers | User / Agent / Org / Tier | accessKey: settings | modules/Settings/components/AccountCampaignSettings/features/CampaignAccessControl/components/CampaignUserAccess | P2
Settings | CampaignQRCode | Yes | ⬜ | Not Started | Page | /user/account/settings/campaignsettings/qrcode | User / Agent / Org / Tier | accessKey: settings | modules/Settings/components/AccountCampaignSettings/features/CampaignQRCode | P2
Settings | CampaignsQRCodeExport | Yes | ⬜ | Not Started | Page | /user/account/settings/campaignsettings/qrcode/exportdetails | User / Agent / Org / Tier | accessKey: settings | modules/Settings/components/AccountCampaignSettings/features/CampaignQRCode/Drawer/partials/CampaignQRCodeExport | P2
SocialMonitor | Social Monitor (whole feature) | No - dead | ⬜ | Excluded | Page | nav advertises /account/socialmonitor | Admin + User | accessKey: social_monitor | modules/SocialMonitor | P2 | 46 files / 7,375 lines / 11 drawers. No route AND no component importer anywhere - only the Redux reducer is mounted. Entirely unreachable today.
WebAnalytics | WebAnalytics | Yes | ⬜ | Not Started | Page | /user/account/webanalytics | User / Agent / Org / Tier | accessKey: web_analytics | modules/WebAnalytics | P2
Widgets | Testimonials widget configuration | No - dead | ⬜ | Excluded | Page | nav advertises /account/widget/testimonials/configuration | Admin + User | n/a | modules/Widgets/submodules/Testimonials | P2 | Nav links to it but NO route exists - falls through to PageNotFound. Confirm with Geetha before dropping.

## Area Summary
Sizing view - route count does not track effort; lines and drawers do
Area | Route entries | Traffic rank | Parity rows | Excluded rows | Files | Lines | Drawers | Modals | Sizing note
(routes infra: PageNotFound) | 4 | P2 | 4 | 0
(shared components) | 2 | P2 | 2 | 0
AIVisibility | 1 | P2 | 1 | 0 | 23 | 4546 | 0 | 0
AbusiveReviews | 1 | P2 | 1 | 0 | 11 | 1886 | 0 | 0
AccountSettings | 2 | P1 | 0 | 2 | 30 | 5633 | 3 | 0
Accounts | 2 | P0 | 2 | 0 | 43 | 6550 | 7 | 2
AdminGroups | 1 | P2 | 1 | 0 | 10 | 979 | 0 | 0
Admins | 2 | P1 | 2 | 0 | 19 | 3014 | 0 | 0
AgentDashboard | 2 | P0 | 2 | 0 | 210 | 32491 | 2 | 2
AgentReviews | 1 | P0 | 1 | 0 | 9 | 1352 | 0 | 0
AgentSettings | 1 | P2 | 1 | 0 | 48 | 8131 | 1 | 1
AppSettings | 16 | P1 | 15 | 1 | 194 | 25662 | 18 | 2
Auth | 35 | P0 | 35 | 0 | 235 | 47266 | 1 | 2 | Very large - budget by lines and drawers, not by route count.
Bundles | 2 | P1 | 2 | 0 | 30 | 2339 | 1 | 1
Campaigns | 13 | P1 | 4 | 9 | 669 | 73974 | 18 | 2 | Very large - budget by lines and drawers, not by route count.
ChatBot | 0 | P2 | 1 | 0 | 13 | 1985 | 0 | 0
DataAndAnalysis | 4 | P1 | 4 | 0 | 33 | 8207 | 4 | 2
GlobalDrawer | 0 | P1 | 1 | 0 | 6 | 365 | 1 | 0
Hierarchy | 3 | P0 | 3 | 0 | 373 | 81271 | 45 | 3 | Very large - budget by lines and drawers, not by route count.
HierarchyDashboards | 6 | P0 | 6 | 0 | 90 | 10496 | 0 | 2
IncompleteSurvey | 8 | P2 | 6 | 2 | 22 | 3798 | 0 | 1
Insights | 1 | P2 | 1 | 0 | 76 | 9010 | 1 | 0
Integrations | 1 | P1 | 1 | 0 | 5 | 643 | 0 | 0
LeaderBoard | 2 | P1 | 2 | 0 | 23 | 3519 | 0 | 0
LearningCenter | 2 | P2 | 2 | 0 | 12 | 2065 | 1 | 0
Listing | 20 | P0 | 20 | 0 | 230 | 28986 | 7 | 1
Listings | 3 | P1 | 3 | 0 | 180 | 26469 | 7 | 1
Mismatches | 2 | P1 | 2 | 0 | 63 | 8785 | 5 | 1
Nav | 0 | P0 | 1 | 0 | 97 | 11458 | 0 | 0
NoConnectionFound | 2 | P2 | 2 | 0 | 1 | 77 | 0 | 0
Notifications | 4 | P1 | 4 | 0 | 9 | 997 | 0 | 0
OnboardingGroupDashboard | 2 | P2 | 2 | 0 | 34 | 3219 | 0 | 0
OrganizationSettings | 2 | P1 | 2 | 0 | 32 | 3852 | 3 | 0
Organizations | 6 | P0 | 6 | 0 | 52 | 10220 | 7 | 0
Page | 0 | P0 | 1 | 0 | 30 | 4467 | 0 | 1
ProductGuide | 0 | P2 | 1 | 0 | 15 | 2879 | 1 | 1
Profile | 8 | P1 | 6 | 2 | 288 | 48520 | 12 | 4 | Very large - budget by lines and drawers, not by route count.
ProfileEnhancement | 8 | P1 | 8 | 0 | 160 | 41165 | 1 | 0 | Very large - budget by lines and drawers, not by route count.
PromotePartners | 1 | P2 | 1 | 0 | 50 | 6536 | 2 | 0
Referrals | 1 | P2 | 1 | 0 | 54 | 8654 | 2 | 1
Reports | 12 | P1 | 12 | 0 | 71 | 14427 | 0 | 0
RequestReview | 1 | P1 | 1 | 0 | 38 | 6317 | 3 | 0
ReviewWidget | 5 | P1 | 5 | 0 | 78 | 10139 | 1 | 0
Reviews | 4 | P0 | 4 | 0 | 86 | 11802 | 3 | 0
Settings | 35 | P0 | 29 | 6 | 332 | 53181 | 39 | 3 | Very large - budget by lines and drawers, not by route count.
SocialMonitor | 0 | P2 | 0 | 1 | 46 | 7375 | 11 | 0 | Unreachable dead feature - excluded, written down not dropped.
Transactions | 7 | P1 | 7 | 0 | 44 | 5391 | 0 | 0
UserManagement | 4 | P0 | 4 | 0 | 132 | 17904 | 11 | 0
WebAnalytics | 1 | P2 | 1 | 0 | 63 | 8109 | 2 | 0
Widgets | 0 | P2 | 0 | 1 | 13 | 1037 | 0 | 1

## Gaps & Decisions
Gaps found while taking the inventory - written down now rather than discovered later
ID | Finding | Evidence | Type | Recommendation | Decision | Decided By | Date
XMP-01 | Full parity across XMP is not reachable in the window | 240 route entries / 43 areas / 220 drawer mount points / 677,148 lines | Scope | Read the card as inventory + top-traffic parity + written gap log. Confirm the bar with Geetha.
XMP-02 | No traffic data available, yet the brief says sequence by traffic | No analytics access; ranking derived from DEFAULT_ROUTES in admin.js:126-127 and user.js:108-113 | Assumption | Treat the P0/P1/P2 column as an assumption. Get Geetha to correct the order before the build starts.
XMP-03 | The new shell is not available on this machine | No tailwind/shadcn/supabase/postgres anywhere; deck slide 16 says the shells exist and are wired | Blocker | Build a local stand-in on the same stack; escalate for real shell access by 20 Sept.
XMP-04 | Agent-assisted campaigns and graph audiences are a different discipline | Deck slide 13 (Campaigns) vs slide 12 (XMP); intake lists Graph as OFF LIMITS | Scope | Port the Campaigns LIST for navigational parity; leave editor, settings and audience to that owner.
XMP-05 | SocialMonitor is entirely unreachable but still shipped | 46 files / 7,375 lines / 11 drawers; no route, no component importer; nav link at Nav/userNavItems.js:1345 | Dead code | Exclude from parity. Confirm with Geetha that no customer reaches it before deleting.
XMP-06 | Testimonials widget config is advertised in nav but has no route | nav path /account/widget/testimonials/configuration; modules/Widgets/submodules/Testimonials | Dead code | Exclude from parity; confirm it is not a capability users lost silently.
XMP-07 | Two route entries embed a query string and can never match | '/account/incompletesurvey?campaignId' in admin.js:585 and user.js:726 | Dead route | Do not port. React Router v5 matches pathname only.
XMP-08 | /account/hierarchy/preview is declared twice per persona file | admin.js:368 and :372; user.js:321 and :346 | Duplicate | Port once. The second entry is unreachable under <Switch>.
XMP-09 | /admin/account and /user/account render a blank page | admin.js:169, user.js:261 - AccountSettings container with no showAccountSetting prop | Dead route | Do not port the route.
XMP-10 | Six nav paths point at URLs with no route, falling through to PageNotFound | socialmonitor (x2), testimonials config (x2), /admin/listing, /admin/tableaumetrics | Bug | Fix in the port by deriving nav from the route table instead of a parallel hand-maintained list.
XMP-11 | Duplicate React key when an agent loads /user/account/reviews | user.js:275-283 and :284-290 both keyed by routePath at AuthRouter.js:159 | Bug | Report upstream to the v2 team; key by componentId in the port.
XMP-12 | Permission gating is implemented twice and can disagree | routes/components/AuthPage.js (accessKey/app/feature) and Nav/components/index.js getAccess() | Architecture | Port as ONE permission concept consumed by both router and nav.
XMP-13 | 83 of 240 route entries are the same screen at a second persona URL | 240 entries vs 157 distinct routePath strings | Opportunity | Build once, mount per persona - this is the single biggest parity saving available.
XMP-14 | Tabs and drawers are invisible to a route census | 0 nested <Route>; 220 drawer mounts; query-string tab states such as /account/insights?tab=Score | Method | Pass 2 must inventory in-screen states for P0 areas or the screen count stays understated.

## Progress & Legend
XMP parity - pass 1 progress
Live formulas over the 'XMP Inventory P1' tab. Update Status there; this updates itself.
Headline
Rows inventoried
In parity scope
Excluded (with a written reason)
Done
% complete (of parity scope)
P0 rows not yet Done
Open gaps awaiting a decision
By Status | Count | % of all
Not Started
In Progress
In Review
Done
Blocked
Excluded
By Traffic rank | Rows | Not Done
P0
P1
P2
Counted facts (cross-checked twice)
Route entries in src/routes/config | 240
Distinct full URLs (with persona prefix) | 237
Distinct routePath strings | 157
Areas | 43
Drawer mount points / modals | 220 / 34
Module files / lines | 4,382 / 677,148
Nested <Route> declarations | 0 - tabs and drawers are state-driven
Legend
Parity required
Yes |  |  | Must exist on the new shell at capability parity.
No - dead |  |  | Unreachable in today's XMP. Excluded, with the evidence on the Gaps tab.
No - duplicate |  |  | A second declaration of a screen already counted.
No - other discipline |  |  | Owned by another builder (Campaigns editor internals, slide 13).
Traffic rank
P0 |  |  | Persona landing routes, sign-in, and global chrome. Build first.
P1 |  |  | Regular multi-persona use.
P2 |  |  | Deep leaf screens, niche auth flows, rare or single-persona admin.
How the rank was derived
Assumption, not data |  |  | No analytics access. P0 is a ROUTE-level allowlist - the routes each persona actually lands on (DEFAULT_ROUTES, admin.js:126-127 and user.js:108-113), plus sign-in and the global chrome. A deep leaf inside a P0 area is NOT P0: /account/settings is P0, /account/settings/campaignsettings/accesscontrol/manageusers is not. Anything 4+ path segments deep, and the niche auth flows, drop to P2. Code mass sizes the work; it does not order it. Geetha to correct this column first.
The rule this sheet enforces
Parity is the floor |  |  | Parity of capability, not of layout. Reproducing a bad screen faithfully is the failure mode. Nothing is silently dropped - anything not ported has a row on the Gaps tab.
Pass 2 (depth) adds |  |  | Actions, Filters, Permission behavior, and Empty/Error/Loading states - for P0 areas only. Accounts is already at that depth in xmp-accounts-inventory.xlsx.